## Schedule
| Host Board Schedule for ANT Latency Testing | [5 empty] | This board can also be used as Range Extender or LIT or GDO
Task# | Task Name | Duration | Start | Finish | Predecessors | Resource Names | Jatin's Comment
| SRBridge-Repeater | 30 days? | 2015-07-06 | 2015-08-14
6 | HRD Creation | [5 empty] | Done
7 | Sch-Draft Release | 1 day | 2015-07-06 | 2015-07-06 |  | Gulrej
8 | Sch Approval | 1 day | 2015-07-07 | 2015-07-07 |  | Akshay
9 | BOM Release | 1 day | 2015-07-07 | 2015-07-07 |  | Gulrej
10 | Component Procurement for 5 proto board quantity | 1 day | 2015-07-09 | 2015-07-09 |  | Kamlesh | Manufacture 5 proto boards to verify hardware design
11 | PCB Design and Gerber Release | 5 days | 2015-07-07 | 2015-07-13 | 7 | Gulrej,Jatin
12 | PCB Proto Manufacturing | 5 days | 2015-07-15 | 2015-07-21 | 11 | Kamlesh | Get quote by 7/13 so can release order on 7/15
13 | PCB Proto Assembly | 2 days | 2015-07-22 | 2015-07-23 | 12 | Kamlesh
14 | Board Bringup and Testing -Router | 1 day | 2015-07-24 | 2015-07-24 | 13 | Gulrej | Hardware design verification
15 | Manufacturing PCB for 250 quantity | 7 days | 2015-07-27 | 2015-08-04 | 14 | Jatin
16 | Plastic Box Purchase | 21 days | 2015-07-07 | 2015-08-04 |  | Jatin,Navy
17 | Assembly of 250# of qty of repeater | 3 days | 2015-08-05 | 2015-08-07 | 15 | Kamlesh | Assuming PCPartner will finish production by 7/31 & Jatin will carry it to Inida by 8/4/15
18 | Testing and Configuration of repeater | 2 days | 2015-08-10 | 2015-08-11 | 17 | Mitesh | Will do at Assembly house
19 | Box Assembly | 2 days | 2015-08-12 | 2015-08-13 | 18 | Mitesh | Will do at Assembly house
20 | Dispatch to Ahmedabad Office | 1 day | 2015-08-14 | 2015-08-14 | 19 | Kamlesh
21 | Testing Jig | 15 days | 2015-07-10 | 2015-07-30 |  | Mitesh | Mitesh will cooridante with Vendor
22 | Define ANT Test setup and procedure |  |  |  |  | Ashok | According to answer we will choose power supply option
23 | Performance testing at Inida office | 10 days | 2015-08-17 | 2015-08-31 | 20 | Ron | Verification of ANT calculator with different test scenarios
24 | Dispatch 240 units to USA | 4 days | 2015-08-31 | 2015-09-05 | 23 | Jatin